## Risks
ICES4HU Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Mitigation Strategy
1 | 2023-04-24 | Failure to schedule | Project failed to meet deadlines. | E | 3 | 30% | 0.9 | Project Manager | Establish precise deadlines and checkpoints, measure progress with project management tools, and provide frequent updates.
2 | 2023-04-24 | Lack of synchronization in team | Team members might not be on the same page as their teammates or their tasks. | P | 3 | 25% | 0.75 | Project Manager | Promote communication, define roles, monitor progress, and make use of tools to spot problems early.
3 | 2023-04-24 | Team members who perform poorly | Overestimating a group member's labor. Thus, giving him more tasks then s/he can perform | P | 4 | 20% | 0.8 | Project Manager | Clarify expectations, provide training and feedback, and, if necessary, replace team members who aren't performing above the standard.
4 | 2023-04-24 | Wrong choice of framework or database | The chosen framework or database is inappropriate. | Te | 4 | 25% | 1 | Software Architect | Before committing to a framework or database, do the research, consult, and test.
5 | 2023-04-24 | Incorrect tools for the project | Using unsuitable tools can lead to decreased productivity, costs, and quality. | To | 3 | 20% | 0.6 | Software Architect | Identify needs, perform research, consult, and select the finest tools for the job.
6 | 2023-04-24 | Miscommunication with stakeholders | Failure to communicate the stakeholders | R | 4 | 30% | 1.2 | Software Analyst | Establish clear communication guidelines for frequency, format, and regular updates to stakeholders.
7 | 2023-04-24 | Not understanding project requirements fully | Improper understanding of project requirements can lead to negative impacts. | R | 4 | 35% | 1.4 | Software Analyst | Gather requirements, assess them, involve stakeholders, then confirm with testing and prototyping.
8 | 2023-04-26 | Defects, bugs, and usability issues affecting user experience | Negative user experience can lead to decreased adoption, satisfaction, and reputational damage. | Te | 4 | 40% | 1.6 | Software Tester | Establish procedures to find and fix problems and issues, conduct extensive testing, and include users.
9 | 2023-04-29 | User error | Users may submit incorrect evaluations, leading to inaccurate data. | P | 3 | 40% | 1.2 | Software Analyst | Create user-friendly user interfaces, provide clear feedback and instructions, check for errors, and put safety measures in place.
10 | 2023-04-29 | Privacy concerns | Personal information can be accessed or shared without consent. | O | 4 | 30% | 1.2 | Software Architect | Implement security measures and comply with privacy laws.
11 | 2023-04-29 | Data loss or corruption | Data can be lost or corrupted, making it difficult to use. | Te | 5 | 20% | 1 | Software Configuration Manager | Implement strong data backup and recovery processes to protect data.
12 | 2023-04-29 | Insufficient maintenance | Inadequate maintenance might result in out-of-date equipment and security flaws | O | 3 | 40% | 1.2 | Software Configuration Manager | Developing and implementing a maintenance plan for web application updates.
13 | 2023-04-29 | Lack of security measures | The platform may be susceptible to hacking attacks, data breaches, and unauthorized access due to weak security measures. | Te | 5 | 75% | 3.75 | Software Architect | Implement strong security measures such as encryption, authentication, access controls, and regular security audits.
14 | 2023-04-29 | Integration issues | The platform may rely on third-party tools or systems that do not integrate seamlessly, causing technical issues and delays in the project | To | 4 | 50% | 2 | Software Tester | Test third-party tools and systems thoroughly, identify potential integration issues early on, and have contingency plans in place.
15 | 2023-04-29 | Resource constraints | The project may face resource constraints, such as limited budget, time, or employee that hinder project progress or quality. | E | 4 | 50% | 2 | Project Manager | Prioritize project goals and requirements, optimize resource allocation, and communicate resource constraints and trade-offs to all stakeholders.
16 | [6 empty] | 0
17 | [6 empty] | 0